## Targets
RFD 2018-19 Achievements vis-à-vis Targets
|  | Upto | 2018-09-01
Sl. No. | Objective | Unit | Targets for the year 2018-19 | Achievements
1 | Overall Avg Turnaround Time (TRT) | Hours | 64 | 60.9
2 | Average Ship Berth Day Output | Tonnes | 9100 | 10115
3 | Overall Volume of Cargo throughput | MMT | 60 | 35.15
4 | Operating Ratio | % | 73.23 | 81.02
5 | Cost Per tonne Handling | Rupees | 190 | 203.49
6 | Operating Surplus | Rupees (In crore) | 440.22 | 167.56
Reduction in Expenditure:
7 | CISF | % | 2 | -9.97
| OTA |  | 2 | 12.97
| Medical Expenditure per person | Rs. |  | 3266.1
| Award of Projects | Nos | 8 | 4 | Ref next sheet for details
8 |  | Investment | 4195.75 | 193.17
(Rs. in crore)
|  | Capacity (MMTPA) | 9.19 | ---
| Completion of Projects | Nos | 7 | 4 | Ref next sheet for details
9 |  | Investment | 920.19 | 67
(Rs. in crore)
|  | Capacity (MMTPA) | 22 | ---
10 | Berth Productivity
| Gross productivity | Gross MT / day |  | Not applicable
(Coal Conventional)
| Gross productivity | Gross MT /day |  | Not applicable
(Coal Mechanised)
| Avg. productivity-Discharge rate (POL) MT/hr | MT/hr. | 3250 | 3161
(Crude Oil)
11 | Pension Liability
Total Accrual value of pension as on 1.4.2018(Rs. Crores)
Unfunded portion of the pension amount (Rs. Crores)
| Target for reduction in Unfunded portion(Rs. Crores) |  | 800 | 432.13
12 | Transshipment of Containers
Share of Transshipment of Containers out of the total containers handled
13 | Coastal Cargo
| Increase in Coastal Cargo |  | 30.00 MMT | 15.42
$ Mumbai Port does not have Container Terminal. It does not receive any container vessel also. It receives about 16000 TEUs by barges and 20000 TEUs by road from JN Port. Very little containers i.e. about 6000 TEUs are received from a few combi vessels.
No transshipment of containers from foreign ports .The figures shown above are transshipped containers from JN Port.

## Status of Projects
Projects for Award in RFD 2018-19
Sl. No. | Name of the Project | Investment | Capacity | Status
|  | (Rs. Crores) | (MTPA)
1 | Offshore Container Terminal | 1290 | 4.19 | Dredging at Berth Pocket completed. Dredging contract awarded to JSCPL terminated due to poor progress. Work of filling up Princes Dock is completed, Victoria Dock is substantially completed. Work of deve-loping RCD is completed. The Work of Dock closure wall at PD 1 is completed and VD is substantially completed, work at PD2 is stopped. There is no progress on dredging front. The Govt. has sanctioned 2nd RCE on 30.09.2015 subject to the condition that the dredging should synchronise with the time of bringing larger ships which require deeper draft (which would warrant the residual dredging). The Project is stalled and is being restructured. The cargo mix for rebidding has been finalised. Meetings with the licensee has been held, to sort out differences bet-ween ICTPL & MbPT on various issues. Chairman held a meeting with Hon'ble Minister of Shipping on 17.08.2016. Vide TR 136/ 2017 of 16.01.2017. the Board has approved restructuring of the project. The proposal hasbeen forwarded to MoS for Govt approval on 03.03.2017. Once the same is approved by the Govt. RFQ will be floated. Meeting under chairmanship of additional Secretary M.O.S. held on 25.05.2017 with Department of Expenditure, Economic affairs, Legal affairs of Niti Aayog. SFC meeting held on 12.09.2017. SFC meeting minutes circulated on 03.10.2017. Draft cabinet note again circulated on 16.11.2017. A meeting held in PMO on 30.1.2018 attended by Secy. Shipping & Chairman, MbPT. A Committee under the CEO Niti-Aayog to finalise the way forward for OCT. Meeting of Committee held on 20.2.2018 Final Meeting of the comittee held on 20.03.2018. Minutes of meeting issued on 28.05.2018
2 | Sewerage treatment plant | 12.58 | - | Tenders due for opening on 15.11.2018.
3 | Evacuation Plan for Port and Ro-Ro Facility | 39 | - | Total 5 works have been identified and all 5 works have been awarded. The work is expected to complete by Nov-Dec 2018 | Awarded
4 | Modernisation of Sassoon Dock Fishing harbour.(Execution by GOM) | 52.17 | - | MFDC has awarded tenders for Civil Works, Construction of Ice- Plant, Auction Hall and Effluent Treatment Plant. | Awarded
5 | Jetty at Girgaon Chowpatty | 10 | - | Tenders will be invited after : i) Allotment of area by MCGM for access to the jetty and ii) receipt of CRZ clearance.
6 | Setting up of Floating Storage Regasification Unit ( FSRU) on PPP | 2690 | 5 | The project is annulled.
| ERP Project | 100 |  | Work awarded to Tech Mahindra by IPA. | Awarded
7
8 | Dredging of channel for BPX and BPS | 2 |  | Awarded & Completed. M/s. Boskalis-JDN (JA) have completed removal of rock pinnacle from the approach channel | Awarded
| TOTAL | 4195.75 | 9.19
Projects for Completion in RFD 2018-19
Sl. No. | Name of the Project | Investment | Capacity | Status
|  | (Rs. Crores) | (MTPA)
1 | Fifth Oil Berth at Jawahar-Dweep | 811 | 22 | Capital dredging work already completed and other works like Civil works , Submarine Pipeline works and Electro mechanical and fire fighting work - are in progress
2 | Development of RO-RO facility at Ferry Wharf. | 30 | - | Work completed on 15.6.2018. | Completed
3 | Domestic Cruise Terminal | 15 | - | Work Completed. | Completed
4 | Lease of waterfront for Floating restaurant | 20 | - | Contract awarded for setting up of 2 floating restaurants on 6.4.2017 and one on 27.06.2017. Two vessels have arrived & are under refurbishment. Will be operational after getting permissions from Navy, Police, MCGM, MPCB & FDA. | Completed
5 | Installation of Access control system. | 12.19 | - | Will be completed by 30th November
6 | Dredging of channel for BPX and BPS | 2 |  | Awarded & Completed. M/s. Boskalis-JDN (JA) have completed removal of rock pinnacle from the approach channel | Completed
Total |  | 890.19 | 22